## Career Skills Assessment
Task | Issue key | Issue Type | Status | Project name | Project type | Project lead | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Due date
Client Requirements Gathering Meeting | SCRUM-17 | Story | In Progress | Career Skills Assessment 2 | software | Luke Kadingo | Medium |  | Allison Li | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:24 | 2025-03-13 15:34 | 2025-04-03 15:00 |  | 2025-03-16
Internal Project Check-In Action Items Summary | SCRUM-16 | Story | In Progress | Career Skills Assessment 2 | software | Luke Kadingo | Medium |  | Abdulfaruq Seriki | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:24 | 2025-03-13 15:38 |  |  | 2025-03-16
Draft Project Plan | SCRUM-15 | Story | Done | Career Skills Assessment 2 | software | Luke Kadingo | Medium | Done | Abdulfaruq Seriki | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:23 | 2025-03-13 15:41 |  | 2025-03-13 15:27 | 2025-03-12
Client Background research | SCRUM-14 | Story | Done | Career Skills Assessment 2 | software | Luke Kadingo | Medium | Done | Richmond Quarshie | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:23 | 2025-03-13 15:41 |  | 2025-03-13 15:27 | 2025-03-12
Requirements Gathering Interview Questions | SCRUM-13 | Story | Done | Career Skills Assessment 2 | software | Luke Kadingo | Medium | Done | Elizabeth Poon | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:23 | 2025-03-13 15:41 |  | 2025-03-13 15:27 | 2025-03-12
Team Contract | SCRUM-12 | Story | Done | Career Skills Assessment 2 | software | Luke Kadingo | Medium | Done | Luke Kadingo | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:22 | 2025-03-13 15:40 |  | 2025-03-13 15:26 | 2025-03-09
Project Roles and Responsibilities Matrix | SCRUM-11 | Story | Done | Career Skills Assessment 2 | software | Luke Kadingo | Medium | Done | Allison Li | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:19 | 2025-03-13 15:38 |  | 2025-03-13 15:19 | 2025-03-09
Sprint 1 | SCRUM-10 | Epic | To Do | Career Skills Assessment 2 | software | Luke Kadingo | Medium |  |  | Abdulfaruq Seriki | Abdulfaruq Seriki | 2025-03-13 15:18 | 2025-03-13 15:37 |  |  | 2025-03-20
Summary | Issue key | Issue id | Issue Type | Project key | Project name | Project type | Project lead | Project description | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Due date | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent

## Career Skills Matrix
Task | Issue key | Issue Type | Status | Project name | Project type | Project lead | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Due date
CLONE - Create Final Deliverable Draft | SCRUM-30 | Task | To Do | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-04-03 14:32 | 2025-04-03 14:32
Create Final Deliverable Draft | SCRUM-29 | Task | To Do | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 15:38 | 2025-04-03 14:32
Form Plans for Visualizations and Graphs based on Findings | SCRUM-28 | Task | To Do | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 15:38 | 2025-04-03 14:33
Begin compiling Skills Matrix and Catalog | SCRUM-27 | Task | To Do | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 15:37 | 2025-04-03 14:33
Individual Project Check-In Self-Assessment 2 | SCRUM-26 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Yann Mbianga | Ojie | Ojie | 2025-03-27 15:19 | 2025-03-27 15:44 | 2025-03-27 15:44
Project Check-In Action Items Summary 2 | SCRUM-25 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Devon O'Neil Wilkes | Ojie | Ojie | 2025-03-27 15:15 | 2025-04-03 14:02 | 2025-04-03 14:02
Project Check-in Meeting 2 | SCRUM-24 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Devon O'Neil Wilkes | Ojie | Ojie | 2025-03-27 15:15 | 2025-03-27 15:45 | 2025-03-27 15:45
Sprint Project Plan 2 | SCRUM-23 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Ojie | Ojie | Ojie | 2025-03-27 15:15 | 2025-04-03 14:02 | 2025-04-03 14:02
Project Plan - Project Initiation | SCRUM-21 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Ojie | Ojie | Ojie | 2025-03-27 15:13 | 2025-03-27 15:34 | 2025-03-27 15:34
Risk Management | SCRUM-19 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Ojie | Ojie | Ojie | 2025-03-27 15:12 | 2025-03-27 15:48 | 2025-03-27 15:48
Project Deliverables Contract | SCRUM-17 | Task | In Progress | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  | Ojie | Ojie | Ojie | 2025-03-27 14:48 | 2025-03-27 15:46
Merge Data Findings with other Career Readiness Group | SCRUM-16 | Task | To Do | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 14:41 | 2025-03-27 14:41
Client Project Work Check-In Zoom Meeting w/ TJ | SCRUM-15 | Task | To Do | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 14:37 | 2025-03-27 14:37
Outline For White Paper Final Deliverable | SCRUM-13 | Task | In Progress | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  | Ojie | Ojie | Ojie | 2025-03-27 14:26 | 2025-03-27 15:46
Conclude on Final Deliverable Medium | SCRUM-12 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done |  | Ojie | Ojie | 2025-03-27 14:25 | 2025-03-27 15:03 | 2025-03-27 15:03
Begin initial designs of Infographics/Visualizations for Career Opportunity Alignments | SCRUM-11 | Task | In Progress | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 14:12 | 2025-04-03 14:02
Compile Database of Resources for Career Opportunities | SCRUM-10 | Task | In Progress | iConsultancy - Career Skills Matrix | software | Ojie | Medium |  |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-27 14:04 | 2025-04-03 14:02
Client Project Work Check-In Zoom Meeting w/ TJ | SCRUM-9 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done |  | Devon O'Neil Wilkes | Devon O'Neil Wilkes | 2025-03-13 14:42 | 2025-04-03 14:02 | 2025-04-03 14:02
Internal Project Check-In Action Items Summary | SCRUM-8 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Ojie | Yann Mbianga | Yann Mbianga | 2025-03-13 14:39 | 2025-03-27 14:08 | 2025-03-27 14:08
Client Requirements Gathering Meeting | SCRUM-7 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Devon O'Neil Wilkes | Yann Mbianga | Yann Mbianga | 2025-03-13 14:38 | 2025-03-27 14:08 | 2025-03-27 14:08
Project Roles and Responsibilities Matrix | SCRUM-5 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Yann Mbianga | Yann Mbianga | Yann Mbianga | 2025-03-13 14:35 | 2025-03-13 14:37 | 2025-03-13 14:35
Team Contract | SCRUM-4 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Evan Hardy | Ojie | Ojie | 2025-03-13 14:34 | 2025-03-13 14:37 | 2025-03-13 14:35
Requirements Gathering Interview Questions | SCRUM-3 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Romeo Alvarenga | Yann Mbianga | Yann Mbianga | 2025-03-13 14:34 | 2025-03-13 14:37 | 2025-03-13 14:35
Draft Project Plan | SCRUM-2 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Devon O'Neil Wilkes | Ojie | Ojie | 2025-03-13 14:34 | 2025-03-13 14:37 | 2025-03-13 14:35
Client Background Research | SCRUM-1 | Task | Done | iConsultancy - Career Skills Matrix | software | Ojie | Medium | Done | Ojie | Yann Mbianga | Yann Mbianga | 2025-03-13 14:34 | 2025-03-13 14:37 | 2025-03-13 14:35

## UX Research and Design-1
Task | Issue key | Issue Type | Status | Assignee | Start date | Inferred start date | Due date | Inferred due date
Finalize User Research | SCRUM-1 | Epic | Done | shannon | 2025-03-13 | 2025-03-13 | 2025-03-23 | 2025-03-23
Google Doc with User Research Based On Meeting Notes | SCRUM-2 | Story | Done | kespinal
Scheduling Recurring Internal Team Meetings | SCRUM-5 | Epic | In Progress | Cideth Oliva | 2025-03-13 | 2025-03-13 | 2025-05-08 | 2025-05-08
Create Jira Timeline | SCRUM-6 | Story | Done | Cideth Oliva
Schedule Meeting with TJ | SCRUM-11 | Story | In Progress | shannon
Schedule Meeting with Justin | SCRUM-12 | Story | Done | shannon
Update Client: Weekly Meetings | SCRUM-7 | Epic | In Progress | Trinity Hill | 2025-03-13 | 2025-03-13 | 2025-05-08 | 2025-05-08
03/13/25 Send Meeting Notes/ Action Items to Client | SCRUM-8 | Story | Done | Trinity Hill |  |  | 2025-03-13
03/27/25 Send Meeting Notes/Action Items to Client | SCRUM-9 | Story | Done | Remington Nelson |  |  | 2025-03-27
04/03/25 Send Meeting Notes/Action Items to Client | SCRUM-10 | Story | Done | Remington Nelson |  |  | 2025-04-03
Low-Fidelity Wireframes | SCRUM-13 | Epic | Done | Cideth Oliva | 2025-03-17 | 2025-03-17 | 2025-03-23 | 2025-03-23
Draft to show Max, Tj, and Justin | SCRUM-14 | Story | In Progress | kespinal
Edit draft based on client input | SCRUM-15 | Story | To Do | Remington Nelson
High-Fidelity Wireframes | SCRUM-16 | Epic | In Progress |  |  |  | 2025-05-08 | 2025-05-08
Organize website layout and pages | SCRUM-18 | Story | In Progress |  |  |  | 2025-05-08

## Client Feedback
Task | Issue key | Issue Type | Status | Project name | Project type | Project lead | Priority | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Due date | Status Category Changed
Research Topics for Survey | SCRUM-6 | Story | To Do | INST 490 Client Feedback Survey | software | Chantoan Ha | Medium |  | Chantoan Ha | Chantoan Ha | 2025-04-03 14:51 | 2025-04-03 14:51 | 2025-04-03 15:04 |  | 2025-04-03 14:51
Evaluate Old Survey | SCRUM-5 | Story | To Do | INST 490 Client Feedback Survey | software | Chantoan Ha | Medium | Chantoan Ha | Chantoan Ha | Chantoan Ha | 2025-04-03 14:51 | 2025-04-03 14:51 |  |  | 2025-04-03 14:51
Final Report | SCRUM-4 | Epic | To Do | INST 490 Client Feedback Survey | software | Chantoan Ha | Medium |  | Chantoan Ha | Chantoan Ha | 2025-04-03 14:50 | 2025-04-03 14:50 |  |  | 2025-04-03 14:50
Sprint 1 : Client Requirements Gathering Meeting | SCRUM-3 | Story | To Do | INST 490 Client Feedback Survey | software | Chantoan Ha | Medium | Robert Dang | Chantoan Ha | Chantoan Ha | 2025-03-13 14:48 | 2025-03-13 14:53 |  | 2025-03-16 | 2025-03-13 14:48
Sprint 1: Internal Project Check-In Action Items Summary | SCRUM-2 | Story | Done | INST 490 Client Feedback Survey | software | Chantoan Ha | Medium | Chantoan Ha | Chantoan Ha | Chantoan Ha | 2025-03-13 14:48 | 2025-03-13 14:55 |  | 2025-03-16 | 2025-03-13 14:55
Sprint 1 | SCRUM-1 | Epic | To Do | INST 490 Client Feedback Survey | software | Chantoan Ha | Medium |  | Chantoan Ha | Chantoan Ha | 2025-03-13 14:47 | 2025-03-13 14:47 | 2025-04-03 15:03 |  | 2025-03-13 14:47

## Client Survery
Task | Issue key | Issue Type | Status | Project key | Project name | Project type | Project lead | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Resolved | Due date | Description | Parent | Parent summary | Status Category | Status Category Changed
Project Epic | CS-21 | Story | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  |  | Duy Nguyen | Duy Nguyen | 2025-03-27 16:08 | 2025-03-27 16:08 |  | 2025-04-08 |  | 10066 | Sprint 2 | To Do | 2025-03-27 16:08
Project Check-in Meeting 2 | CS-20 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Mia Leandri | Duy Nguyen | Duy Nguyen | 2025-03-27 14:59 | 2025-03-27 15:10 | 2025-03-27 15:10 | 2025-04-04 |  | 10066 | Sprint 2 | Done | 2025-03-27 15:10
Risk Management | CS-19 | Story | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  | moumarou | Duy Nguyen | Duy Nguyen | 2025-03-27 14:51 | 2025-03-27 14:52 |  | 2025-04-04 |  | 10066 | Sprint 2 | To Do | 2025-03-27 14:51
Individual analysis of questions and what to change | CS-18 | Story | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  | Mia Leandri | Duy Nguyen | Duy Nguyen | 2025-03-27 14:48 | 2025-03-27 14:52 |  | 2025-04-04 |  | 10066 | Sprint 2 | To Do | 2025-03-27 14:48
Come up with a new delivery method | CS-17 | Story | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  | Adam Zaidi | Duy Nguyen | Duy Nguyen | 2025-03-27 14:47 | 2025-03-27 14:52 |  | 2025-04-04 |  | 10066 | Sprint 2 | To Do | 2025-03-27 14:47
Schedule second meeting with TJ regarding sprint two action items and solutions | CS-16 | Story | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  | Aadarsh Bandyopadhyay | Duy Nguyen | Duy Nguyen | 2025-03-27 14:47 | 2025-03-27 14:52 |  | 2025-04-04 |  | 10066 | Sprint 2 | To Do | 2025-03-27 14:47
Client Background Research | CS-15 | Story | Plan | CS | Client Survey | software | Duy Nguyen | Medium |  | moumarou | Duy Nguyen | Duy Nguyen | 2025-03-27 14:41 | 2025-03-27 14:55 |  | 2025-04-07 |  | 10066 | Sprint 2 | In Progress | 2025-03-27 14:55
Individual Project Check-In Self-Assessment 2 | CS-14 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Duy Nguyen | Duy Nguyen | Duy Nguyen | 2025-03-27 14:41 | 2025-04-01 00:03 | 2025-04-01 00:03 | 2025-03-31 |  | 10066 | Sprint 2 | Done | 2025-04-01 00:03
Sprint Project Plan 2 | CS-13 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Mia Leandri | Duy Nguyen | Duy Nguyen | 2025-03-27 14:33 | 2025-03-27 14:51 | 2025-03-27 14:49 | 2025-03-31 |  | 10066 | Sprint 2 | Done | 2025-03-27 14:49
Sprint 2: Internal Project Check-In Action Items Summary Copy | CS-12 | Story | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  | Adam Zaidi | Duy Nguyen | Duy Nguyen | 2025-03-27 14:31 | 2025-03-27 14:51 |  | 2025-03-31 |  | 10066 | Sprint 2 | To Do | 2025-03-27 14:31
Sprint 2 | CS-11 | Epic | To Do | CS | Client Survey | software | Duy Nguyen | Medium |  |  | Duy Nguyen | Duy Nguyen | 2025-03-27 14:31 | 2025-03-27 14:31 | [5 empty] | To Do | 2025-03-27 14:31
Team Contract | CS-10 | Epic | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Mia Leandri | Duy Nguyen | Duy Nguyen | 2025-03-16 14:12 | 2025-03-16 14:24 | 2025-03-16 14:15 | 2025-03-08 |  |  |  | Done | 2025-03-16 14:15
Internal Project Check-In Action Items Summary | CS-9 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Mia Leandri | Duy Nguyen | Duy Nguyen | 2025-03-16 14:10 | 2025-03-16 14:24 | 2025-03-16 14:16 | 2025-03-16 |  | 10033 | Sprint 1 | Done | 2025-03-16 14:16
Draft Project Plan | CS-8 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Adam Zaidi | Duy Nguyen | Duy Nguyen | 2025-03-16 14:10 | 2025-03-16 14:24 | 2025-03-16 14:16 | 2025-03-12 |  | 10033 | Sprint 1 | Done | 2025-03-16 14:16
Client Background Research | CS-7 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Aadarsh Bandyopadhyay | Duy Nguyen | Duy Nguyen | 2025-03-16 14:10 | 2025-03-16 14:24 | 2025-03-16 14:16 | 2025-03-12 |  | 10033 | Sprint 1 | Done | 2025-03-16 14:16
Client Requirements Gathering Meeting | CS-6 | Story | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | moumarou | Duy Nguyen | Duy Nguyen | 2025-03-16 14:10 | 2025-03-16 14:24 | 2025-03-16 14:16 | 2025-03-16 |  | 10033 | Sprint 1 | Done | 2025-03-16 14:16
Project Roles and Responsibilities Matrix | CS-5 | Epic | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Aadarsh Bandyopadhyay | Duy Nguyen | Duy Nguyen | 2025-03-16 14:06 | 2025-03-16 14:24 | 2025-03-16 14:15 | 2025-03-08 |  |  |  | Done | 2025-03-16 14:15
Sprint 1 | CS-4 | Epic | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | moumarou | Duy Nguyen | Duy Nguyen | 2025-03-16 14:04 | 2025-03-16 14:24 | 2025-03-16 14:15 | 2025-03-16 |  |  |  | Done | 2025-03-16 14:15
Sprint 1 : Client Background Research | CS-3 | Task | Done | CS | Client Survey | software | Duy Nguyen | Medium | Done | Adam Zaidi | Duy Nguyen | Duy Nguyen | 2025-03-14 14:41 | 2025-03-16 14:22 | 2025-03-16 14:15 |  | Delivering a valued outcome that addresses your client's problem or need starts with knowing who your client is and what is important to them. Using readily available resources including the scope of work, perform background research on your client and their particular problem or need. What do they do? Who are their stakeholders? What is their mission or business strategy? How does their problem or need fit into what they do? Be sure to also look at how similar organizations function to learn more about the overall market. Your research will likely be incomplete. Make a note of questions you have about the organization and the project as your are doing your initial investigation. These questions will become the basis for the [+client requirements gathering questions+¦https://umd.instructure.com/courses/1382510/assignments/7107908] you will develop prior to meeting with your client for the first time. Submit a summary of your client background research for feedback from the instructional team. |  |  | Done | 2025-03-16 14:15

## InfoGov
Key | Issue Type | Parent | Summary | Status | Assignee | Start date | Inferred start date | Due date | Inferred due date | Issue color
KAN-10 | Epic |  | Team Formation | Done |  |  |  | 2025-03-13 | 2025-03-13 | purple
KAN-1 | Task | KAN-10 | Project Roles & Responsibilities Matrix | Done | Megan Cha |  |  | 2025-03-06 | 2025-03-06 | purple
KAN-2 | Task | KAN-10 | Team Contract | Done |  |  |  | 2025-03-09 | 2025-03-09 | purple
KAN-8 | Epic |  | Sprint 1 | Done |  | 2025-03-01 | 2025-03-01 | 2025-03-16 | 2025-03-16 | purple
KAN-3 | Task | KAN-8 | Requirements Gathering Interview Questions | Done |  |  |  | 2025-03-06 | 2025-03-06 | purple
KAN-4 | Task | KAN-8 | Client Background Research | Done |  |  |  | 2025-03-06 | 2025-03-06 | purple
KAN-5 | Task | KAN-8 | Draft Project Plan | Done |  |  |  | 2025-03-12 | 2025-03-12 | purple
KAN-6 | Task | KAN-8 | Client Requirements Gathering Meeting | Done | Geoffrey Zhang |  |  | 2025-03-16 | 2025-03-16 | purple
KAN-7 | Task | KAN-8 | Internal Project Check-In Action Items Summary | Done | Daniel Zarrelli |  |  | 2025-03-16 | 2025-03-16 | purple
KAN-9 | Epic |  | Sprint 2 | To Do |  |  |  |  | 2025-04-01 | purple
KAN-14 | Task | KAN-9 | Risk Assessment | Done | Megan Cha |  |  | 2025-04-01 | 2025-04-01 | purple
KAN-16 | Task | KAN-9 | Procedure Doc for Clients (Secure Share) | Done | Arvin Torabazari |  |  | 2025-04-01 | 2025-04-01 | purple
KAN-17 | Task | KAN-9 | Procedure Doc for Students (Secure Share) | Done | Arvin Torabazari |  |  | 2025-04-01 | 2025-04-01 | purple
KAN-13 | Task | KAN-9 | Sprint Project Plan 2 | Done |  |  |  | 2025-03-31 | 2025-03-31 | purple
KAN-19 | Task | KAN-9 | Project Check-In Action Items Summary 2 | Done | Daniel Zarrelli |  |  | 2025-03-31 | 2025-03-31 | purple
KAN-12 | Task | KAN-9 | Individual Project Check-In Self Assessment 2 | Done |  |  |  | 2025-03-31 | 2025-03-31 | purple
KAN-11 | Task | KAN-9 | Internal Project Check-In Action Items Summary | Done | Daniel Zarrelli |  |  | 2025-03-31 | 2025-03-31 | purple
KAN-15 | Task | KAN-9 | Recurring Meeting w/ TJ 3/28/2025 | Done |  |  |  | 2025-03-28 | 2025-03-28 | purple
KAN-18 | Task | KAN-9 | Policy Document (Data Classification) | In Progress | Geoffrey Zhang |  |  | 2025-04-01 | 2025-04-01 | purple
KAN-24 | Epic |  | KAN-10 Sprint 3 | Idea |  |  |  |  | 2025-04-16 | purple
KAN-22 | Task | KAN-24 | Sprint 3: Internal Project Check-in Meeting | Done |  |  |  | 2025-04-16 | 2025-04-16 | purple
KAN-23 | Task | KAN-24 | Sprint 3: Internal Project Check-in Action Items Summary | Done |  |  |  | 2025-04-16 | 2025-04-16 | purple
KAN-21 | Task | KAN-24 | Sprint 3: Project Plan | Done |  |  |  | 2025-04-16 | 2025-04-16 | purple
KAN-25 | Epic |  | Sprint 4 | Idea |  |  |  |  | 2025-04-20 | purple
KAN-26 | Task | KAN-25 | Sprint 4: Project Plan | Done | [5 empty] | purple
KAN-27 | Task | KAN-25 | Sprint 4: Internal Client Meeting Notes | To Do |  |  |  | 2025-04-20 | 2025-04-20 | purple
KAN-28 | Task | KAN-25 | Sprint 4: Internal Project Check-in Meeting | To Do |  |  |  | 2025-04-20 | 2025-04-20 | purple
KAN-30 | Task | KAN-25 | Sprint 4: Internal Project Check-In Action Items Summary | To Do |  |  |  | 2025-04-20 | 2025-04-20 | purple
KAN-29 | Task | KAN-25 | Sprint 4: Client Meeting Summary & Survey | To Do |  |  |  | 2025-04-20 | 2025-04-20 | purple

## Social Media Strategy
Summary | Issue key | Issue Type | Status | Project key | Project name | Project type | Project lead | Priority | Resolution | Assignee | Reporter | Reporter Id | Creator | Created | Updated | Resolved | Due date | Watchers
Decide color scheme | KAN-13 | Subtask | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:30 | 2025-03-27 15:14 | 2025-03-27 15:13 |  | Aakash Sathish
Decide what needs to be posted | KAN-12 | Subtask | In Progress | KAN | Social Media Strategy | software | Nicolette Hood | Medium |  |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:30 | 2025-03-27 15:16 |  |  | Aakash Sathish
Decide on social media platforms | KAN-11 | Subtask | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:30 | 2025-03-27 15:16 | 2025-03-27 15:16 |  | Nicolette Hood
plan biweekly meeting with client | KAN-10 | Subtask | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:24 | 2025-03-25 09:56 | 2025-03-25 09:56 |  | Sarah Peng
Create jira timeline | KAN-9 | Subtask | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:24 | 2025-03-25 09:56 | 2025-03-25 09:56 |  | Sarah Peng
Meet with client | KAN-8 | Subtask | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:24 | 2025-03-16 20:51 | 2025-03-16 20:50 |  | Sarah Peng
Spring 3 Assignments | KAN-7 | Task | To Do | KAN | Social Media Strategy | software | Nicolette Hood | Medium |  | Sarah Peng | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:22 | 2025-03-16 17:35 |  | 2025-04-20 | Sarah Peng
Sprint 2 Assignments | KAN-6 | Task | In Progress | KAN | Social Media Strategy | software | Nicolette Hood | Medium |  | Aakash Sathish | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-16 17:22 | 2025-03-16 17:35 |  | 2025-04-07 | Sarah Peng
Sprint 1 Assigments | KAN-5 | Task | In Review | KAN | Social Media Strategy | software | Nicolette Hood | Medium |  | Gurlal Dhaliwal | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-13 14:47 | 2025-03-16 17:35 |  | 2025-03-23 | Sarah Peng
Client meeting | KAN-4 | Task | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done | Kirk Mensah | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-13 14:47 | 2025-03-16 17:35 | 2025-03-16 17:33 |  | Sarah Peng
Social Media Strategy | KAN-3 | Epic | Idea | KAN | Social Media Strategy | software | Nicolette Hood | Medium |  |  | Sarah Peng | 712020:2065b9ed-ca4c-4ab3-8f32-8a88f0e72d2a | Sarah Peng | 2025-03-13 14:47 | 2025-03-16 17:31 |  | 2025-05-02 | Sarah Peng
Client Meeting | KAN-2 | Epic | Done | KAN | Social Media Strategy | software | Nicolette Hood | Medium | Done |  | Gurlal Dhaliwal | 712020:89edefef-dd6a-4dd2-98db-4da885beffc3 | Gurlal Dhaliwal | 2025-03-13 14:34 | 2025-03-16 14:46 | 2025-03-16 14:46 | 2025-03-14 | Gurlal Dhaliwal
Meeting with Client @4 | KAN-1 | Task | To Do | KAN | Social Media Strategy | software | Nicolette Hood | Medium |  | Kirk Mensah | Nicolette Hood | 712020:9eb62ae9-7e45-4fde-bc8b-f45a5988c22c | Nicolette Hood | 2025-03-13 14:34 | 2025-03-16 17:35 |  | 2025-03-24 | Nicolette Hood